## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1454 | OSM Performance Report missing Object descriptorType | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com | agarcia@whitestack.com | 2021-02-25 17:49 | CURRENT | 2021-02-25 17:49 | CURRENT | 2021-07-08 17:41 | comment | 2021-11-29 16:28 | RECENT | 1 | 0 |  |  | 2
| DEVOPS | 1473 | OSM operator charms optimization (tox.ini, .jujuignore, flake8) | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-03-17 15:24 | CURRENT | 2021-03-17 15:24 | CURRENT |  | comment | 2021-03-17 15:24 | CURRENT | 1 | 0
| IM-NBI | 1557 | Multiple VNFs using same VNFD ID at NSD can't connect to different networks | Master | OPEN-UNCONFIRMED | glavado@whitestack.com | fbravo@whitestack.com | 2021-06-03 17:23 | CURRENT | 2021-06-03 17:23 | CURRENT | 2021-07-08 17:36 | comment | 2021-11-29 16:29 | RECENT | 1 | 0 |  |  | 1
| Devops | 1702 | NG-UI container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:39 | CURRENT | 2021-10-14 20:39 | CURRENT | 2021-10-14 20:52 | assigned_to | 2021-10-14 20:52 | CURRENT | 1 | 0 |  | 1 | 2
| Devops | 1704 | LCM container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:41 | CURRENT | 2021-10-14 20:41 | CURRENT | 2021-10-14 20:52 | assigned_to | 2021-10-14 20:52 | CURRENT | 1 | 0 |  | 1 | 2

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1123 | NS Instantiate nsName as required property [sol005robot] | v7.0 | OPEN-UNCONFIRMED | frank.bryden@etsi.org | jmguzman@whitestack.com | 2020-07-06 15:05 | CURRENT | 2020-07-06 15:05 | CURRENT | 2021-09-02 11:32 | assigned_to | 2021-09-02 11:32 | CURRENT | 1 | 0 |  |  | 2
| N2VC | 1234 | OSM reports successful deployment when a charm relation fails | v8.0 | OPEN-UNCONFIRMED | endika.aldecoa@ehu.eus |  | 2020-09-25 12:29 | CURRENT | 2020-09-25 12:29 | CURRENT |  | comment | 2021-12-07 20:37 | RECENT | 1 | 0
| RO | 1416 | OSM doesn't return a deployment error description in some cases | v9.0 | OPEN-UNCONFIRMED | daguilarh@indra.es |  | 2021-01-22 12:34 | CURRENT | 2021-01-22 12:34 | CURRENT |  | cc | 2021-01-22 12:34 | CURRENT | 1 | 0
| LCM | 1425 | NG-RO unable to pin VNF with vim_account config | v9.0 | OPEN-UNCONFIRMED | agarcia@whitestack.com | fbravo@whitestack.com | 2021-01-28 16:54 | CURRENT | 2021-01-28 16:54 | CURRENT | 2021-03-15 16:55 | comment | 2021-07-19 22:40 | CURRENT | 1 | 0 |  | 1 | 1
| RO | 1427 | Sometimes netslice instances remains indefinitely in "init" operational status | v9.0 | CONFIRMED | daguilarh@indra.es | eduardo.sousa@canonical.com | 2021-02-01 17:51 | CURRENT | 2021-10-13 10:05 | CURRENT | 2021-02-02 18:49 | resolution | 2021-10-13 10:05 | CURRENT | 4 | 1 |  | 1 | 1
| OSMClient | 1428 | k8scluster-update command does not work | v9.0 | OPEN-UNCONFIRMED | alimonj@indra.es | mark.beierl@canonical.com | 2021-02-02 11:54 | CURRENT | 2021-02-02 11:54 | CURRENT | 2021-11-29 16:34 | component | 2021-11-29 16:34 | RECENT | 1 | 0 |  | 1 | 1
| DEVOPS | 1451 | High memory consumption in MongoDB process | v9.0 | CONFIRMED | daguilarh@indra.es | mark.beierl@canonical.com | 2021-02-25 13:05 | CURRENT | 2021-02-25 13:43 | CURRENT | 2021-02-25 13:43 | comment | 2021-03-09 09:55 | CURRENT | 2 | 0 |  | 1 | 1
| IM-NBI | 1453 | Instantiation parameters with keys "x.y" are not allowed | v9.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-02-25 15:56 | CURRENT | 2021-02-25 15:56 | CURRENT |  | comment | 2021-02-25 15:56 | CURRENT | 1 | 0
| N2VC | 1461 | K8scluster-create seems to be doing a synced task | v9.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-03-04 12:42 | CURRENT | 2021-03-04 12:42 | CURRENT |  | short_desc | 2021-03-04 15:48 | CURRENT | 1 | 0
| N2VC | 1541 | OSM does not report K8s issues when deploying KDUs | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-05-26 09:51 | CURRENT | 2021-05-26 09:51 | CURRENT |  | comment | 2021-05-26 09:51 | CURRENT | 1 | 0
| Robot-tests | 1546 | Missing E2E test for subscription API client | Master | OPEN-UNCONFIRMED | daguilarh@indra.es |  | 2021-05-27 11:36 | CURRENT | 2021-05-27 11:36 | CURRENT |  | cc | 2021-05-27 11:38 | CURRENT | 1 | 0
| N2VC | 1551 | All LXD proxy charms use the same series | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-05-28 12:32 | CURRENT | 2021-05-28 12:32 | CURRENT |  | comment | 2021-05-31 19:58 | CURRENT | 1 | 0
| LCM | 1552 | Dockerfile.local not working fine | Master | OPEN-UNCONFIRMED | daguilarh@indra.es |  | 2021-05-28 13:29 | CURRENT | 2021-05-28 13:29 | CURRENT |  | cc | 2021-05-28 13:29 | CURRENT | 1 | 0
| RO | 1597 | Sometimes netslice instances remains indefinitely in "init" operational status | v10.0 | CONFIRMED | eduardo.sousa@canonical.com |  | 2021-07-15 11:51 | CURRENT | 2021-12-03 10:09 | RECENT |  | resolution | 2021-12-03 10:09 | RECENT | 3 | 1
| RO | 1598 | Sometimes netslice instances remains indefinitely in "init" operational status | Master | UNCONFIRMED | eduardo.sousa@canonical.com |  | 2021-07-15 11:52 | CURRENT | 2021-08-10 10:03 | CURRENT |  | comment | 2021-08-10 10:08 | CURRENT | 5 | 2
| RO | 1603 | Dummy VIM fails in HA configuration | v10.0 | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2021-07-23 16:10 | CURRENT | 2021-07-23 16:10 | CURRENT |  | comment | 2021-07-23 16:10 | CURRENT | 1 | 0
| N2VC | 1631 | Cannot add instantiation parameters for Juju bundles (KNF) | v10.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:51 | CURRENT | 2021-08-09 16:51 | CURRENT |  | comment | 2021-08-09 16:51 | CURRENT | 1 | 0
| RO | 1640 | Error at create vdu: 'NoneType' object does not support item assignment | Master | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2021-08-24 14:08 | CURRENT | 2021-08-24 14:08 | CURRENT |  | cc | 2021-08-24 14:09 | CURRENT | 1 | 0
| LCM | 1646 | Error when performing scale_out of an instance using execution environment | v10.0 | OPEN-UNCONFIRMED | paula.encinar@atos.net |  | 2021-08-26 15:26 | CURRENT | 2021-08-26 15:26 | CURRENT |  | comment | 2021-08-26 15:26 | CURRENT | 1 | 0
| IM-NBI | 1752 | NBI does not validate manifest hashes from SOL004/SOL007 packages | v11.0 | OPEN-UNCONFIRMED | fbravo@whitestack.com | fbravo@whitestack.com | 2021-11-10 15:33 | CURRENT | 2021-11-10 15:33 | CURRENT | 2021-11-25 15:33 | cc | 2021-11-25 15:33 | CURRENT | 1 | 0 |  |  | 1
| RO | 1769 | GCP connector doesn't provide internet access for management network | v11.0 | OPEN-UNCONFIRMED | sgallardor@indra.es | sgallardor@indra.es | 2021-11-15 11:53 | CURRENT | 2021-11-15 11:53 | CURRENT | 2021-11-15 12:48 | dependson | 2021-11-26 10:05 | CURRENT | 1 | 0 |  |  | 1

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1188 | Uploading NSD content of NSD in state 'ONBOARDED' [sol005robot] | v7.0 | IN_PROGRESS | frank.bryden@etsi.org | jmguzman@whitestack.com | 2020-08-10 16:34 | CURRENT | 2020-08-14 09:00 | CURRENT | 2021-09-02 11:34 | assigned_to | 2021-09-02 11:34 | CURRENT | 2 | 0 |  |  | 3
| PLA | 1213 | vnf_price_list.yaml with prices per project contains an unnecessary sequence collection in the yaml file | v8.0 | OPEN-UNCONFIRMED | lars-goran.magnusson@arctoslabs.com |  | 2020-09-17 09:28 | CURRENT | 2020-09-17 09:28 | CURRENT |  | comment | 2020-09-17 09:28 | CURRENT | 1 | 0
| Robot-tests | 1217 | Warning when executing basic_13-ns_relations.robot Robot test | v8.0 | OPEN-UNCONFIRMED | daguilarh@indra.es |  | 2020-09-21 11:42 | CURRENT | 2020-09-21 11:42 | CURRENT |  | comment | 2021-12-07 20:32 | RECENT | 1 | 0 |  | 1
| Robot-tests | 1218 | Warning when executing basic_14-vnf_relations.robot Robot test | v8.0 | OPEN-UNCONFIRMED | daguilarh@indra.es |  | 2020-09-21 11:44 | CURRENT | 2020-09-21 11:44 | CURRENT |  | comment | 2021-12-07 20:32 | RECENT | 1 | 0 |  | 1
| N2VC | 1266 | Error on using object type parameter for actions from OSM | v8.0 | OPEN-UNCONFIRMED | preethika.p@tataelxsi.co.in |  | 2020-10-19 06:41 | CURRENT | 2020-10-19 06:41 | CURRENT |  | comment | 2020-10-19 06:41 | CURRENT | 1 | 0
| Bugzilla | 1269 | Clean up of old bugs | unspecified | OPEN-UNCONFIRMED | silvia.almagia@etsi.org |  | 2020-10-20 17:13 | CURRENT | 2020-10-20 17:13 | CURRENT |  | comment | 2020-10-20 17:13 | CURRENT | 1 | 0
| MON | 1271 | active vnf indicators in grafana dashboard | v10.0 | CONFIRMED | tolga.golelcin@telenity.com |  | 2020-10-28 07:10 | CURRENT | 2021-07-15 15:59 | CURRENT |  | version | 2021-07-15 15:59 | CURRENT | 2 | 0 | 1
| IM-NBI | 1280 | Support of IPv6 in pdu.yaml | v10.0 | CONFIRMED | anirudh.gupta@hsc.com | gerardo.garciadeblas@telefonica.com | 2020-11-05 07:28 | CURRENT | 2021-10-26 16:53 | CURRENT | 2021-10-26 17:26 | blocked | 2021-12-02 16:53 | RECENT | 2 | 0 | 1 |  | 2
| NBI | 1301 | Hardcoded credentials in code | v8.0 | OPEN-UNCONFIRMED | javier.ramon@telefonica.com | mark.beierl@canonical.com | 2020-11-27 15:55 | CURRENT | 2020-11-27 15:55 | CURRENT | 2021-10-26 16:44 | target_milestone | 2021-10-26 16:44 | CURRENT | 1 | 0 |  | 1 | 1
| NBI | 1305 | Remove self-signed SSL certificate from NBI | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | mark.beierl@canonical.com | 2020-12-01 19:19 | CURRENT | 2020-12-01 19:19 | CURRENT | 2021-10-26 16:44 | cc | 2021-10-26 16:44 | CURRENT | 1 | 0 |  | 1 | 1
| NG-UI | 1346 | NG-UI: cookie-0.3.1 / cookie-0.4.0 | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | barath.r@tataelxsi.co.in | 2020-12-03 01:37 | CURRENT | 2020-12-03 01:37 | CURRENT | 2021-08-10 17:17 | component | 2021-08-10 17:17 | CURRENT | 1 | 0 |  | 1 | 1
| NG-UI | 1347 | NG-UI: faye-websocket-0.10.0 | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | barath.r@tataelxsi.co.in | 2020-12-03 01:38 | CURRENT | 2020-12-03 01:38 | CURRENT | 2021-08-10 17:17 | component | 2021-08-10 17:17 | CURRENT | 1 | 0 |  | 1 | 1
| NG-UI | 1348 | NG-UI: npm-user-validate-1.0.0 | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | barath.r@tataelxsi.co.in | 2020-12-03 01:39 | CURRENT | 2020-12-03 01:39 | CURRENT | 2021-08-10 17:17 | component | 2021-08-10 17:17 | CURRENT | 1 | 0 |  | 1 | 1
| DEVOPS | 1366 | 413 Error - Entity Too Large | v8.0 | OPEN-UNCONFIRMED | ragavi.d@tataelxsi.co.in |  | 2020-12-09 09:02 | CURRENT | 2020-12-09 09:02 | CURRENT |  | comment | 2020-12-09 09:02 | CURRENT | 1 | 0
| NG-UI | 1420 | UI composes new VNF/NS package not in SOL006 format | v9.0 | OPEN-UNCONFIRMED | alexander.onnikov@xored.com | barath.r@tataelxsi.co.in | 2021-01-27 07:35 | CURRENT | 2021-01-27 07:35 | CURRENT | 2021-11-29 16:35 | component | 2021-11-29 16:35 | RECENT | 1 | 0 |  | 2 | 2
| LCM | 1443 | No info about the VDUs in VDU_SCALE_INFO parameter in scaling config actions | v9.0 | OPEN-UNCONFIRMED | alimonj@indra.es |  | 2021-02-18 10:06 | CURRENT | 2021-02-18 10:06 | CURRENT |  | comment | 2021-03-15 15:49 | CURRENT | 1 | 0
| N2VC | 1468 | Cannot remove k8s cluster in some cases | v9.0 | OPEN-UNCONFIRMED | daguilarh@indra.es | david.garcia@canonical.com | 2021-03-16 11:06 | CURRENT | 2021-03-16 11:06 | CURRENT | 2021-07-20 18:02 | component | 2021-07-20 18:02 | CURRENT | 1 | 0 |  | 1 | 1
| LCM | 1487 | Group coordinator failure issue is coming in between LCM and KAFKA often | v8.0 | CONFIRMED | vijay.r@tataelxsi.co.in |  | 2021-03-29 16:47 | CURRENT | 2021-07-20 00:16 | CURRENT |  | everconfirmed | 2021-07-20 00:16 | CURRENT | 2 | 0
| RO | 1497 | Limitations in the multi-site deployment in OSM R9.0 | v9.0 | CONFIRMED | jbaranda@cttc.es | eduardo.sousa@canonical.com | 2021-04-13 07:42 | CURRENT | 2021-07-19 23:10 | CURRENT | 2021-07-19 23:10 | everconfirmed | 2021-07-19 23:10 | CURRENT | 2 | 0 |  | 1 | 1
| IM-NBI | 1507 | Translation of NSDs is dropping VNFFG | v9.0 | OPEN-UNCONFIRMED | agarcia@whitestack.com | agarcia@whitestack.com | 2021-04-15 18:52 | CURRENT | 2021-04-15 18:52 | CURRENT | 2021-07-08 17:42 | priority | 2021-07-08 17:42 | CURRENT | 1 | 0 |  |  | 1
| OSMClient | 1519 | osm package-translate not working for descriptors containing EE config | v9.0 | OPEN-UNCONFIRMED | paula.encinar@atos.net |  | 2021-04-28 16:39 | CURRENT | 2021-04-28 16:39 | CURRENT |  | comment | 2021-04-28 16:39 | CURRENT | 1 | 0
| N2VC | 1528 | LCM/N2VC error deploying KNF with 10 KDUs | v9.0 | CONFIRMED | garomero@indra.es |  | 2021-05-06 10:19 | CURRENT | 2021-12-07 22:18 | RECENT |  | everconfirmed | 2021-12-07 22:18 | RECENT | 2 | 0
| DEVOPS | 1530 | OSM installer bug: install failure when default interface has more than one IPv4 address | v9.0 | CONFIRMED | dreibh@simula.no |  | 2021-05-07 12:52 | CURRENT | 2021-12-07 22:18 | RECENT |  | comment | 2021-12-09 15:18 | RECENT | 2 | 0
| DEVOPS | 1531 | OSM installer bug: check for "curl" package fails | v9.0 | CONFIRMED | dreibh@simula.no |  | 2021-05-07 13:06 | CURRENT | 2021-12-07 21:34 | RECENT |  | target_milestone | 2021-12-09 15:53 | RECENT | 2 | 0
| LCM | 1534 | EE pods are not decomissioned along with VNF | v9.0 | CONFIRMED | guillermo.gomez.external@atos.net | fbravo@whitestack.com | 2021-05-12 15:19 | CURRENT | 2021-05-12 22:01 | CURRENT | 2021-08-02 14:58 | component | 2021-08-02 14:58 | CURRENT | 2 | 0 |  | 2 | 2
| N2VC | 1539 | Helm won't work in airgap environment. Stable repo is not reachable | v9.0 | IN_PROGRESS | david.garcia@canonical.com |  | 2021-05-21 13:47 | CURRENT | 2021-05-24 12:28 | CURRENT |  | comment | 2021-05-24 12:28 | CURRENT | 2 | 0
| IM-NBI | 1548 | Unable to download on boarded NSD in package format. | v9.0 | OPEN-UNCONFIRMED | saikiran.k@tataelxsi.co.in |  | 2021-05-28 09:07 | CURRENT | 2021-05-28 09:07 | CURRENT |  | comment | 2021-05-28 09:07 | CURRENT | 1 | 0
| IM-NBI | 1549 | nslcm ns instances create api expects VIM account in payload. | v9.0 | OPEN-UNCONFIRMED | saikiran.k@tataelxsi.co.in |  | 2021-05-28 09:19 | CURRENT | 2021-05-28 09:19 | CURRENT |  | comment | 2021-05-28 09:19 | CURRENT | 1 | 0
| DEVOPS | 1561 | ci_stage_3.groovy format does not pass groovy linting | v10.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-06-03 18:26 | CURRENT | 2021-06-03 18:26 | CURRENT |  | version | 2021-07-08 17:23 | CURRENT | 1 | 0 | 2
| DEVOPS | 1562 | Not possible to set log level for the modules during installation | v10.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-06-03 18:31 | CURRENT | 2021-06-03 18:31 | CURRENT |  | comment | 2021-09-02 12:03 | CURRENT | 1 | 0
| DEVOPS | 1563 | Stage3 does not archive containers logs when OSM is not healthy | v10.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-06-03 18:36 | CURRENT | 2021-06-03 18:36 | CURRENT |  | comment | 2021-06-22 17:51 | CURRENT | 1 | 0
| RO | 1564 | RO constantly communicates with Openstack VIM even if RO is idle | v8.0 | CONFIRMED | vijay.r@tataelxsi.co.in |  | 2021-06-04 09:00 | CURRENT | 2021-06-04 17:33 | CURRENT |  | comment | 2021-06-16 17:20 | CURRENT | 2 | 0
| Gerrit | 1566 | Jenkins verified votes are not registering | unspecified | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2021-06-07 18:24 | CURRENT | 2021-06-07 18:24 | CURRENT |  | cc | 2021-07-05 17:44 | CURRENT | 1 | 0
| RO | 1576 | configured MAC address parameter is not equal to VM interface | v9.0 | OPEN-UNCONFIRMED | bilal.sharifeh@gmail.com |  | 2021-06-18 15:28 | CURRENT | 2021-06-18 15:28 | CURRENT |  | comment | 2021-06-21 09:15 | CURRENT | 1 | 0
| common | 1577 | NF/NS packages are not removed from LCM when the NS or NF is deleted | v9.0 | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com |  | 2021-06-18 17:02 | CURRENT | 2021-06-18 17:02 | CURRENT |  | comment | 2021-06-18 17:02 | CURRENT | 1 | 0
| LCM | 1579 | Error read ns record from database when execute action in function _on_update_n2vc_db | Master | OPEN-UNCONFIRMED | cuongbo97@gmail.com |  | 2021-06-21 12:52 | CURRENT | 2021-06-21 12:52 | CURRENT |  | comment | 2021-06-21 12:52 | CURRENT | 1 | 0
| DEVOPS | 1581 | Full_instas.sh do not remove osm-ım and osm-devops | v10.0 | OPEN-UNCONFIRMED | mehmet.basar@ulakhaberlesme.com.tr |  | 2021-06-21 13:42 | CURRENT | 2021-06-21 13:42 | CURRENT |  | comment | 2021-06-21 13:42 | CURRENT | 1 | 0
| N2VC | 1584 | Failure updating the ns state with distributed VCA | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-06-22 11:27 | CURRENT | 2021-06-22 11:27 | CURRENT |  | comment | 2021-06-22 11:27 | CURRENT | 1 | 0
| RO | 1588 | Error deleting VIM | v9.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2021-07-06 11:20 | CURRENT | 2021-07-06 11:20 | CURRENT |  | cc | 2021-07-06 11:21 | CURRENT | 1 | 0
| RO | 1607 | the interface position is not taken into account | v10.0 | OPEN-UNCONFIRMED | endika.aldecoa@ehu.eus |  | 2021-07-26 16:55 | CURRENT | 2021-07-26 16:55 | CURRENT |  | priority | 2021-07-26 17:22 | CURRENT | 1 | 0
| OSMClient | 1611 | Error deleting VNFD by name | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | fbravo@whitestack.com | 2021-07-29 10:56 | CURRENT | 2021-07-29 10:56 | CURRENT | 2021-07-29 16:21 | assigned_to | 2021-07-29 16:21 | CURRENT | 1 | 0 |  |  | 1
| LCM | 1621 | Execution enviroment not being created at initial deployment | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr | emin.aktas@ulakhaberlesme.com.tr | 2021-07-30 16:03 | CURRENT | 2021-07-30 16:03 | CURRENT | 2021-08-04 10:45 | comment | 2021-09-09 08:56 | CURRENT | 1 | 0 |  |  | 1
| Unknown | 1622 | Status report not consistent between NS and VNF | v10.0 | OPEN-UNCONFIRMED | guillermo.gomez.external@atos.net |  | 2021-08-02 10:41 | CURRENT | 2021-08-02 10:41 | CURRENT |  | comment | 2021-08-02 10:41 | CURRENT | 1 | 0
| N2VC | 1623 | Lost connection: Error registering native charm | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-03 16:39 | CURRENT | 2021-08-03 16:39 | CURRENT |  | comment | 2021-08-03 16:39 | CURRENT | 1 | 0
| LCM | 1629 | OSMLCM_VCA_ENABLEOSUPGRADE not working | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr |  | 2021-08-06 16:14 | CURRENT | 2021-08-06 16:14 | CURRENT |  | comment | 2021-08-06 16:14 | CURRENT | 1 | 0
| N2VC | 1630 | Cannot add instantiation parameters for Juju bundles (KNF) | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:50 | CURRENT | 2021-08-09 16:50 | CURRENT |  | comment | 2021-08-09 16:51 | CURRENT | 1 | 0
| N2VC | 1632 | Cannot add instantiation parameters for Juju bundles (KNF) | v9.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:52 | CURRENT | 2021-08-09 16:52 | CURRENT |  | comment | 2021-08-09 16:52 | CURRENT | 1 | 0
| RO | 1644 | 'Error at create vdu: unknown' when instantiating network slice | v10.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2021-08-26 14:57 | CURRENT | 2021-08-26 14:57 | CURRENT |  | blocked | 2021-09-02 10:49 | CURRENT | 1 | 0
| RO | 1645 | 'Error at create vdu: unknown' when instantiating network slice | v9.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2021-08-26 15:03 | CURRENT | 2021-08-26 15:03 | CURRENT |  | cc | 2021-08-26 15:03 | CURRENT | 1 | 0
| DEVOPS | 1648 | Microstack initialization failure during charmed installation | v10.0 | CONFIRMED | fsoldatos@ubitech.eu |  | 2021-09-01 12:25 | CURRENT | 2021-12-08 15:18 | RECENT |  | comment | 2021-12-09 14:49 | RECENT | 2 | 0
| RO | 1649 | 'Error at create vdu: unknown' when instantiating network slice | Master | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2021-09-02 10:49 | CURRENT | 2021-09-02 10:49 | CURRENT |  | comment | 2021-09-02 10:49 | CURRENT | 1 | 0
| IM-NBI | 1660 | PATCH of /ns_descriptors/{nsdInfoId} returns wrong HTTP code[sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-14 17:26 | CURRENT | 2021-09-14 17:26 | CURRENT |  | comment | 2021-09-14 17:26 | CURRENT | 1 | 0
| IM-NBI | 1661 | _id vs id [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-14 17:30 | CURRENT | 2021-09-14 17:30 | CURRENT |  | comment | 2021-09-14 17:30 | CURRENT | 1 | 0
| DEVOPS | 1662 | Controller OSM not found; Unix Socket Permission Denied | v10.0 | OPEN-UNCONFIRMED | tayloreisman2012@gmail.com | mark.beierl@canonical.com | 2021-09-15 01:07 | CURRENT | 2021-09-15 01:07 | CURRENT | 2021-09-15 02:04 | comment | 2021-09-16 16:51 | CURRENT | 1 | 0 |  | 1 | 1
| LCM | 1663 | VNF scale-in number of instance to 0 though VNF reached min number of instance | v10.0 | OPEN-UNCONFIRMED | manhvd.hust@gmail.com |  | 2021-09-15 06:01 | CURRENT | 2021-09-15 06:01 | CURRENT |  | comment | 2021-09-16 12:09 | CURRENT | 1 | 0
| IM-NBI | 1667 | PATCH of Individual Package should return 200 [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-16 17:09 | CURRENT | 2021-09-16 17:09 | CURRENT |  | comment | 2021-09-16 17:09 | CURRENT | 1 | 0
| IM-NBI | 1668 | VNFPkgInfo contains more fields than required by default [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-16 17:10 | CURRENT | 2021-09-16 17:10 | CURRENT |  | comment | 2021-09-16 17:10 | CURRENT | 1 | 0
| IM-NBI | 1671 | Absence of id [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:51 | CURRENT | 2021-09-20 21:51 | CURRENT |  | comment | 2021-09-20 21:51 | CURRENT | 1 | 0
| IM-NBI | 1672 | Returned data on NsInstance creation does not conform [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:52 | CURRENT | 2021-09-20 21:52 | CURRENT |  | comment | 2021-09-20 21:52 | CURRENT | 1 | 0
| IM-NBI | 1673 | Launching multiple NS instances with single on-boarded NSD/VNFD just by varying values of IM's fields at NS instantiation time | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:53 | CURRENT | 2021-09-20 21:53 | CURRENT |  | comment | 2021-09-20 21:53 | CURRENT | 1 | 0
| RO | 1677 | Support for Antiaffinity groups | v10.0 | IN_PROGRESS | frodriguezg@indra.es |  | 2021-09-28 18:34 | CURRENT | 2021-11-25 15:30 | CURRENT |  | bug_status | 2021-11-25 15:30 | CURRENT | 2 | 0
| Devops | 1708 | PLA container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:44 | CURRENT | 2021-10-14 20:44 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  | 1 | 2
| Devops | 1709 | Keystone container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:45 | CURRENT | 2021-10-14 20:45 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| Devops | 1710 | Zookeeper container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| Devops | 1711 | Kafka container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| Devops | 1712 | MongoDB container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:47 | CURRENT | 2021-10-14 20:47 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| Devops | 1713 | MySQL container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:48 | CURRENT | 2021-10-14 20:48 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1714 | Hangs on 'Waiting for storageClass' | v10.0 | OPEN-UNCONFIRMED | tayloreisman2012@gmail.com |  | 2021-10-15 18:47 | CURRENT | 2021-10-15 18:47 | CURRENT |  | comment | 2021-11-04 15:53 | CURRENT | 1 | 0